2018-2019 Final report

New Brunswick Wildlife Trust Fund

Nashwaak Watershed Association Inc.

1 March 2019

# 2018-2019 Final report

## Project Name:

Upstream-Downstream Youth Education Program, Erosion Youth Education Program

## Executive summary

The Nashwaak Watershed Association Inc. (NWAI) received $12,000 (?) from the NB Wildlife Trust Fund in the 2018-2019 fiscal year for our education program. Match funding was provided by the Atlantic Salmon Conservation Foundation (?). The project aimed to educate both students and the general public about the native species and natural habitats found within the Nashwaak watershed, while promoting environmentally friendly behavior. All objectives were met or surpassed within the time frame of the grants. The project started in May 2018 and wrapped up in February 2019. Something about budget: ______________________. Moving forward, NWAI will continue this program as funding opportunities arise.

## Objectives

The objectives of the project were to work with elementary schools in the watershed, the general public, and afterschool and summer programs from the Fredericton area to:

- Increase awareness about wetland ecosystems.

- Provide examples to youth of restoration projects with the goal of re-establishing critical habitat for wildlife along the Nashwaak River.

- Encourage youth to identify wetland habitat and reduce stressors to wetlands and wildlife.

- Build knowledge of the river and engagement with the local community.

- Collaborate with the Falls Brook Centre, The Ville Cooperative, NB Department of Environment and Local Government, Department of Energy and Resource Development, the Nature Conservancy of Canada, and the Nature Trust of NB.

- Demonstrate the benefits of protecting and restoring wetland habitat through the Marysville Flats demonstration site.

- Educate youth about erosion, and methods of preventing erosion.

## Performance Measures

All of these objectives were met or exceeded through interactive in-class programming & field trips, hosting & attending public events, and social media outreach. Performance was based on the following:

- # of elementary students that took part in the activity

- # of classes taking part in the activity

- # of schools taking part in the activity

- # of participants at the Critter Dipping Workshops

- # of participants in The Forest Ranger Summer Camp program

- # of participants in The Ville Cooperative summer day camp program

- # of participants Nashwaaksis Public Library and the Fredericton Public Library summer programs.

## Results

We developed and delivered science curriculum-based programming to over 550 grade 3 & 4 students, reaching all 6 elementary schools in the watershed for the first time, plus one just adjacent (Figures 1-3). Details are listed in Table 1.

Table 1: Programming delivered to schools in & around the watershed.

| Date | School | Program | # of Classes | # of Students |
| --- | --- | --- | --- | --- |
| June 4, 2018 | Chief Harold Sappier | Intro to Watersheds | 1 | 16 |
| June 4, 2018 | Chief Harold Sappier | Erosion | 1 | 12 |
| June 8, 2018 | Nashwaak Valley School | Intro to Watersheds | 2 | 40 |
| June 12, 2018 | Stanley Consolidated School | Intro to Watersheds | 1 | 12 |
| Totals | 4 |  | 5 | 80 |

We also delivered other community events & programs, including delivering outdoor education programming to The Ville Cooperative’s ReCONNECT summer camps, and the Maritime College of Forestry Technology ‘Forest Ranger’ Summer Camp, hosting activities at the Nashwaaksis Public Library and the Fredericton Public Library, and hosting or attending various outreach events (Figures 4-16). Details are listed in Table 2.

Table 2: Community event & program details.

| Date | Event | Participants |  | # of Participants |
| --- | --- | --- | --- | --- |
| May 16, 2018 | Birding and Wildlife Photography Workshop | Community members | 50 |  |
| May 25, 2018 | Tree Planting and Live Willow Staking | Fredericton North Rotary Club, Maritime College of Forest Technology, Siemens Canada, community members | 35 |  |
| June 29, 2018 | The Ville ReCONNECT Summer Camp Program | Children ages 5-12 | 30 |  |
| July 6, 2018 | Forest Ranger Summer Camp Program | Children ages 9-12 | 12 |  |
| July 7, 2018 | Boyce Farmers Market | Community members | 75 |  |
| July 11, 2018 | Critter Dipping Workshop | Community members | 23 |  |
| July 21-22, 2018 | Tay Creek Folk Festival | Community members | 35 |  |
| July 25, 2018 | Forest Ranger Summer Camp Program | Children ages 9-12 | 22 |  |
| July 25, 2018 | Critter Dipping Workshop | Community members | 34 |  |
| July 31, 2018 | Fredericton Public Library Test Drive a Job | Children ages 7-12 | 13 |  |
| August 2, 2018 | Fredericton Public Library Story Time | Community members | 40 |  |
| August 7, 2018 | Nashwaaksis Public Library Story Time | Children ages 5-10 | 10 |  |
| August 15 | The Ville ReCONNECT Summer Camp Program | Children ages 5-12 | 18 |  |
| August 17-19, 2018 | Stanley Fair | Community members | 60 |  |

Although not listed as a performance measure, we also worked to increased our social media presence by creating educational content, sharing information, and engaging with our ‘followers’. Examples of this include our #WatershedWordoftheWeek facebook posts (Figure 17) & other social media posts. (Figure 18). In doing so we have managed to steadily increase our social media followers:

  - Facebook: ___ followers (up from 643 in March 2018)

  - Instagram: ___ followers (up from 109 in March 2018)

  - Twitter: ___ followers (up from 401 in March 2018)

The geocaching tour of the Nashwaak river is also an activity funded by this grant. The tour consists of seven geocaches located along the municipal walking trail that runs parallel to the river, beginning at its confluence with the Saint John and continuing upstream along the into Penniac. Our original goal was to have ten geocache locations, but due to technical issues, we currently only have seven. See Figure 19 for a map of cache locations. Each cache is listed on the database with information about NWAI, the river, and a small write-up about each specific location. See Appendix 1 for all database and cache write-ups. The physical caches contain a small logbook, pen, NB Wildlife Trust Fund pencils and conservation plate postcard, and a small write-up about that location (See Figure 20).

### Evaluation

After each visit with a school, either in-class or field trip, we provide the teachers with a feedback form to fill out if they wish to help us fine-tune and further develop our programming. An example, with feedback, is attached.

### Time Frame of Project

The original timeframe of the project was to be April 1st 2017 to March 31st 2018, however due to funding delays and subsequent restraints on staffing, the project did not begin until May 1st 2017. Similarly, due to funding constraints towards the end of the fiscal year, staffing shortages required us to wrap up the project early (Feb 1st 2018). This being said, we are happy with the results we were able to achieve in this timeframe.

### Permits

No permits were required for this project.

### promotion of the NB Wildlife trust fund

We have acknowledged the NB Wildlife Trust Fund as a funder of this project on several occasions, including on our annual newsletter (see attached), which is distributed to 11,000 households and businesses; on social media; at our annual general meeting held in November attended by over 70 members; and on a sign, which we display at all organization events. We also hand out NBWTF pencils to students and at events.

### conclusions

We believe that the project had, and will continue to have, the intended socio-economic and environmental impacts. By engaging with both students and the general public, our aim has been to educate the community about the native species and unique habitats found in the Nashwaak Watershed in order to elicit support for environmental conservation and positive changes in behavior. In particular, by engaging students we are working to create a new generation of environmentally-minded citizens to carry on and expand the work being done by conservationists across the province.

Based on the success of this program, we plan to continue this program in 2019-2020, as funding allows. We will continue to deliver our school programming at its current capacity, and are working to expand the public outreach components as a means of engaging a broader cross-section of the community.

### Attatched documents

| Document | Summary |
| --- | --- |
| 2018 Newsletter | Summary of the work done by the NWAI in 2018 with thanks to our funders. |
| Teacher Feedback Form | Filled out by teachers after a classroom visit or field trip. |

Submitted by:

Figure 1: Students examine benthic macroinvertebrates that they have collected while “Critter Dipping”.

Figure 2: One of the thank you letters we received from a student.

Figure 3: A thank you letter from a teacher.

Figure 4: Forest Ranger campers learning about about a watershed through our “Watershed Model” activity.

Figure 5: Forest Ranger campers participating in our “Silver Maple Benefits” activity.

Figure 6: A group of campers brainstorming on how to prevent erosion during our “Erosion Engineers” activity.

Figure 7: The poster for the Birding and Wildlife Photography Workshop.

Figure 8: Workshop participants learning about Arielle DeMerchant’s tips for birding and wildlife photography, before heading out in the field.

Figure 9: Workshop participants using their new knowledge about birding and wildlife photography.

Figure 10: Volunteers from Fredericton North Rotary Club, Maritime College of Forest Technology, Siemens Canada, and community members that participated in our Tree Planting and Live Willow Staking event.

Figure 11: Posters for our Critter Dipping Workshops.

Figure 12: NWAI staff, Kristin MacKenzie, giving a demonstration on some of the benthic macroinvertebrates that participants had found during the first Critter Dipping Workshop.

Figure 13: Two of our youngest participants admiring the critters that had been found during the second Critter Dipping Workshop.

Figure 14: NWAI Project Assistants, Claire Ferguson and Hannah Sharpe, making a guest appearance on Joy FM 96.5 to promote the organization and upcoming workshops/events.

Figure 15: Hannah and Claire at the Fredericton Boyce Farmers Market.

Figure 16: Claire promoting the NB Wildlife Trust Fund Conservation plates at the Tay Creek Folk Festival.

Figure 17: Two examples of our #WatershedWordoftheWeek social media posts.

Figure 18: Examples of other social media posts.

Figure 19: Location of the caches for Geocache Tour of the Nashwaak.

Figure 20: An example of a geocache with its contents.

Appendix 1

| Cache | Cache information |
| --- | --- |
| Data Base | This is the (first, second, third, etc.) geocache in a series of caches that direct players on a tour of the Nashwaak Watershed, a beautiful and environmentally significant area that stretches from Nashwaak Lake in Central New Brunswick all the way to the confluence of the Nashwaak River with the Saint John River. |
| 1 | A "watershed" is the term used to refer to all of the land that drains into one area or body of water. The Nashwaak Watershed encompasses all of the land in which rivers, streams, brooks, ponds, lakes, wetlands, meltwater, groundwater and runoff drain into the Nashwaak River. As you may have noticed, the Nashwaak River empties into the Saint John River, meaning that it is also part of a bigger watershed, the Saint John River Watershed! |
| 2 | Welcome to Hyla Park! Hyla Park Nature Preserve is a beautiful public area of the Nashwaak Watershed, with walking and biking trails, fantastic views and plenty of biodiversity! If you keep heading up this trail you will have a great view of a beaver lodge! Beavers are what is known as a “keystone species;” a species on which ecosystems depend, and would change drastically if this species were removed. Beavers, by damming water sources, have the capacity to completely transform an ecosystem! |
| 5 | Welcome to the Marysville Flats! This area is the primary location for the Nashwaak Watershed's planting and restoration projects! The flats are a retired hayfield, that was originally a silver maple floodplain forest. NWAI is working to return the area to its original ecosystem by planting silver maple trees throughout the flats. The benefits of re-establishing the native floodplain forest are many! Some of the most notable are re-establishing natural habitat for many species, increasing floodwater uptake by silver maple trees and mitigating spring flood damages, tree roots stabilizing the soil and preventing erosion, and carbon uptake and sequestration from the atmosphere. |
| 6 | Welcome to The Ville! This area is the location of the Nashwaak Watershed Association offices, and provides a great resource for fun outdoor, eco-friendly and sustainable activities in the Marysville area! From here, you have access to many walking, hiking and biking paths along the Nashwaak, as well as river access for swimming, fishing and boating! |
| 8 | The Nashwaak Watershed Association is working to establish a Greenway along the Nashwaak from Marysville to the confluence with the Saint John River in Fredericton. The Greenway will be a forest, trail and wetland area maintained as a centrepiece of natural landscape. It will serve to help maintain the natural balance and offset the environmental strains induced by growth and development on the landscape, and offer unlimited opportunity for natural, outdoor recreation! |
| 9 | This forested floodplain area is key to the mitigation of flooding and the filtration of runoff before it enters the river. Keeping a healthy riparian zone (the area within a few meters of the water) is vital to a maintaining a healthy river system and watershed! Property owners with waterfront property will help both themselves and the environment by keeping a several meter buffer of native grasses, trees and shrubs along the riverbank instead of clearing down to the water. |
| 10 | Agriculture is one of the most common land uses along the Nashwaak River. Upstream from this spot, the watershed consists mainly of agricultural lands and forested lands. Due to the high presence of agriculture along the river, erosion is a major issue along the Nashwaak. The clearing of agricultural lands up to the water’s edge without a riparian buffer contributes to the high rates of riverbank erosion. |